## Group Members
Group Members | Roles | Sorumluluk Özeti
Yasin Kaya Küçükbaş | Frontend(UI)Developer | React/Flutter arayüz kodlaması, kullanıcı giriş ekranları ve dashboard tasarımı.
Yusuf Erdem Doğan | Backend Developer | Coding the carbon footprint calculation algorithm, managing the MongoDB/Firebase database.
Taha Berke Kılıç | Analist&Test | Drawing of UML diagrams, risk management plan and final tests of the project.
Emirhan Kartal | Project Manager | Jira monitoring, progress reporting, frontend and backend integration.

## Project Overview
Project Name | Week | Planned Activities | Output (Deliverable)
GreenTrace :Personal Carbon Footprint Tracker | Week 1 | Team setup, creating Jira and Google Teams accounts, adding the instructor as a watcher.Drawing UML diagrams (Class/Use Case) with draw.io. | Organization Completed
| Week 2 | Requirements analysis | Design Files
Project Description | Week 3 | Establishing the database schema and laying the foundations for the Backend API (Registration/Login). | Database Ready
| Week 4 | Frontend interface coding and development of calculation forms. | First Interface
| Week 5 | Backend and frontend integration; inclusion of the carbon calculation algorithm in the system. | Working Prototype
| Week 6 | Final tests will be conducted, the project will be uploaded to GitHub, and UBIS submission will be completed. | Final Delivery
It is an application that records users' daily activities such as transportation, nutrition, and energy consumption, calculates their environmental impact (CO2 emissions), and raises awareness.

## Budget Planning
Resource Category | Items / Description | Estimated Cost
Project Management | Jira (Atlassian), Google Workspace | $0.00 (Free/Student)
Development Tools | VS Code, GitHub, Node.js, React | $0.00 (Open Source
Database & Hosting | MongoDB Atlas (Free Tier), Firebase | $0.00 (Free Plan)
Design & UML | draw.io, Figma | $0.00 (Free)
Hardware | Personal Laptops & Mobile Devices | Provided by Members
Total Monetary Budget |  | $0.00
Activity / Task | Estimated Time (Hours) | Assigned Members
Planning & Management | 6 Hours | Emirhan(PM), Berke
System Design & UML | 15 Hours | Berke (Analyst), Yasin
Backend Development | 48 Hours | Erdem (Lead), Emirhan
Frontend Development | 48 Hours | Yasin(Lead), Emirhan
Testing & Quality Assurance | 15 Hours | Berke, Emirhan
TOTAL EFOR (Man-Hours) | 132 Hours | 4 Members